## swe573Fall2016
Task Name | Start Date | End Date | Duration | Predecessors | % Complete | Status | Assigned To | Comments
Documentation | 2016-10-14 | 2016-10-18 | 2.5d |  | 14% | In Progress | Can TUKSAVUL
RSD | 2016-10-14 | 2016-10-18 | 2.5d |  | 14% | In Progress | Can TUKSAVUL
Create user scenarios | 2016-10-14 | 2016-10-14 | 1d |  | 50%
Parse user scenarios | 2016-10-17 | 2016-10-17 | 0.25d | 3
Create Entity Perspective | 2016-10-17 | 2016-10-17 | 0.25d | 4
Create Role Perspective | 2016-10-17 | 2016-10-17 | 0.25d | 4
Create Page Perspective | 2016-10-17 | 2016-10-17 | 0.25d | 4
Create use case diagram | 2016-10-17 | 2016-10-17 | 0.5d | 5, 6
Create mockups | 2016-10-17 | 2016-10-18 | 1d | 6
DSD
Architecture
Component Diagram
API
Development | 2016-10-20 | 2016-11-27 | 27d |  | 83% | In Progress | Can TUKSAVUL
Explore NDB API | 2016-10-20 | 2016-10-21 | 2d
Decide on a system/component architecture | 2016-10-24 | 2016-10-28 | 5d |  | 100%
Initiate Flask | 2016-10-29 | 2016-10-31 | 2d |  | 100%
Initiate Typescript | 2016-11-01 | 2016-11-04 | 4d |  | 100%
Initiate webpack | 2016-11-04 | 2016-11-09 | 4d |  | 100%
Initiate Angular 2 | 2016-11-16 | 2016-11-21 | 4d |  | 100%
Code Phase 1 | 2016-11-24 | 2016-11-27 | 2d
Create Landing Page
Create Navbar
Create User Profile Section
Set up client side routing
Create Register Page
Create Forgot Password Page
Create Login Page
Make an user/register request to backend | 2016-11-27 | 2016-11-27 | 1d
Make an user/logn request to backend | 2016-11-26 | 2016-11-26 | 1d
Create User backend API | 2016-11-25 | 2016-11-25 | 1d
Database | 2016-11-24 | 2016-11-24 | 1d
Create MySQL Database | 2016-11-24 | 2016-11-24 | 1d
Tie Mysql with sql alchemy | 2016-11-24 | 2016-11-24 | 1d
Request/register users
Deploy to Amazon
Code Phase 2
Connect to NDB API
Analyze NDB API
Wrap NDB API
Make requests to NDB API
Create Enter Foods Section
Create Select Box with Suggestion
Save entered foods to database
Create Select Box with Suggestions
Create Enter Exercise Section
Save Entered Exercise to Database
Code Phase 3
Reporting Epic
Code Phase 4
Create Email Service
Send user verification
Make API key request for individual users
Testing
Frontend Tests
API Tests
Front end beautification
Project Management | [5 empty] | In Progress | Can TUKSAVUL
Update time tracking
Update smartsheet
Export Gantt PERT chart
Export Burndown chart
Create weekly report | [7 empty] | Description of the work ▪ Category/Type of work (UI, research, development,... ) ▪ estimated time ▪ actual time ▪ status ◦ Cumulative work until present date: ▪ estimated ▪ actual ▪ category/type
Set up client-side routing | 2016-11-27T20:45:52Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create User Profile Section | 2016-11-27T20:44:44Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create Navbar | 2016-11-27T20:43:54Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create Landing Page | 2016-11-27T20:41:59Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create Login Page | 2016-11-27T20:47:44Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create Forgot Password Page | 2016-11-27T20:47:21Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0
Create Register Page | 2016-11-27T20:46:45Z |  | 2016-12-05T00:00:00Z |  |  |  |  | 0

## Comments
Row 1 | Sample Discussion Need help? E-mail us at support@smartsheet.com or call us at 425.283.1870 | Todd Jones | 08/28/13 10:58 PM
| This is a sample discussion. Discussions will let you track comments about a particular line item or sheet. Many customers paste relevant emails into a discussion as well. | Todd Jones | 08/28/13 10:59 PM